## Sheet1
ID | Task/Feature | Description | Isaac | Janek | Ander | Ching-Ting
1 | Comprehensive Game Storyline creation | The story behind the game, description of characters, evidence questions and try again feedbacks, collection of evidence locations in Dresden |  | x | x
2 | Creation of descirptions and text | Creation of all final texts and descriptions for the app |  |  | x
3 | Sketches/AI-driven UI design with Midjourney | Creation of UI elements in Midjourney with initial style |  | x
4 | 16 Figma UI designs | initial UI layouts | x |  |  | x
5 | Base application theme creation | Developed the basic android app with the agreed colors, look and feel of buttons, to enable us work with the same UI | x
6 | Map Design | Customized google maps to match with our design |  | x
7 | Button icon design | Designed the icon of button |  |  |  | x
8 | Generation of all the images for the app with AI | All of the images were created using Midjourney |  | x
9 | Modification of characters images | To modify the images Adobe Photoshop software was used |  |  |  | x
10 | Generation of App icon with AI | Writing multiple prompts in Midjourney to create initial idea of app icon |  | x
11 | Design of App icon | Designed the App icon on Inkscape based on the AI generated pictures |  |  | x
12 | Icon and Photoshop modifications | Making images professionally presentable |  |  |  | x
13 | Database Creation | The sqlite database to handle the state of the application | x | x | x | x
14 | Interaction with database and app | Creation of Database Helper class, connecting map view with database |  | x
15 | Map View Java programming | The connection between the mapview and other activities |  | x
16 | Java programming of evidence list | Cretion of evidence list class together with recycle view and adapters |  | x |  | (x): the old evidence list control, but deleted in the end
17 | Map zoom in and zoom out | The button of zoom in and zoom out create |  |  |  | x
18 | Logic to unlock next location and Vibration | The state managment of the application |  | x
19 | Shaking notification of icon | Adding the shaking effect to the evidence list icon |  |  | x
20 | Java programming to enable sound | The interactive sound feature | x |  | x
21 | Layout designs for introduction | Designed the starting page of the app to start the game |  |  |  | x
22 | Layout designs for newspaper | Designed the newspaper page for explain what had happened in the story |  |  |  | x
23 | 6 Layout designs for evidence list items | Designed xml layouts for 6 evidence list items. The activity that is shown when an evidence list item is clicked | x
24 | Java programming for 6 evidence list items | Added interactivity to all 6 evidence list activities including item onClick events, questions dialogs and changing UI based on question responses | x |  | x | x
25 | 4 Layout designs for suspects | Designed xml layouts for the 4 suspects | x
26 | Layout design for the Who Is Guilty activity | Designed xml layout for the Who Is Guilty activity | x
27 | Layout design for final output message | Designed the final pages for all correct and incorrect answers when choosing the suspect with explanations |  |  | x
28 | Layout design for plot twist page | Designed the page for the message where the user is asked to gather the last evidence |  |  | x
29 | Fixing Technical Errors | Collective ideas to debug errors | x | x | x | x
30 | Creting all the audios for application | Audios for narrative and suspects were created using AI tool |  | x
31 | Generating the font for the whole app | To make the font same in the whole app |  |  |  | x
32 | Generate all the text into string file | Stored all the text in string and recalled it in layout | x |  | x | x
33 | Putting all the initial individual projects together | Tasked to put all separate android projects together for internal review |  |  |  | x
34 | Makign the app work throughout the whole life cycle | Fixing and adding funcionality related to life cycle of the app | x | x
35 | Merging project | Merging separate project into one application, updating final app |  | x
36 | Publishing to Google PlayStore | Handled the deployment to Google Play Store | x
37 | Testing of the app |  | x | x | x | x